## Sheet1
CLASS 3300 INTRO TO SOFTWARE ENGINEERING
TEAM: | Monetally
REQ MGR: | name: Ryan Rupakheti
DATE: | 2025-11-28 | (Finalized)
Monetally Requirements
|  | Initial Programming |  |  |  | TEST |  |  |  | Outstanding Issues |  | Final DELIVERY |  | Comments
|  | Team Members |  | Date Planned | Date Delievered | Test Method | Test Plan | Team Member | Date Tested |  | # Flags Resolved
ID | REQUIREMENT |  | INC/Ver | [6 empty] | # Flags |  | Ver | Test date
0.1 | Account
0.1.1 | ->UI Design and Intial Implemenation | Jeffrey and Josh | 1.1 | 2025-10-10 | 2025-10-10 | Observe | - | Roy | 2025-10-11 | 0 | 0 | 1.15 | 2025-10-11
0.1.2 | -> Setup Page | Josh | 1.2 | 2025-11-28 | 2025-10-23 | Unit Test | Test Plan 4 | Roy | 2025-10-26 | 0 | 0 | 1.25 | 2025-10-26
0.1.3 | -> Input Salary & Expensese | Roy | 1.3 | 2025-10-30 | 2025-11-03 | Unit Test | Test Plan 1+2 | Roy | 2025-11-05 | 1 | 1 | 1.35 | 2025-11-05 | Restructured Transaction Object
0.1.4 | ->Setting Expense Priority | NO ONE |  |  | NEVER |  |  |  |  | 1 | 0 |  |  | Not Implemented
0.2 | Notifcations
0.2.1 | -> Notify user about upcoming expenses | Jeffrey and Ryan | 2.1 | 2025-10-30 | 2025-10-30 | Unit Test | Test Plan 3 | Roy | 2025-10-31 | 0 | 0 | 2.15 | 2025-10-31
0.2.2 | -> Text Notifications | NO ONE |  |  | NEVER |  | Test Plan 3 |  |  | 1 | 0 |  |  | Not Implemented
0.3 | Analysis
0.3.1 | -> Graph for monthly spending | Roy | 3.1 | 2025-11-26 | 2025-11-26 | Unit Test | Test Plan 5+6 | Roy | 2025-11-27 | 2 | 2 | 3.15 | 2025-11-27 | Minor bug fixes
0.3.2 | -> Set allowance by-month | Josh | 3.2 | 2025-11-10 | 2025-11-10 | Unit Test | Test Plan 10 | Roy | 2025-11-12 | 1 | 1 | 3.25 | 2025-11-12 | Minor bug fixes
0.4 | Misc/Undecided Features (Not Requirements)
0.4.1 | -> Tax calculator | NO ONE |  |  | NEVER |  |  |  |  | 1 | 0 |  |  | Not Implemented
0.4.2 | -> Settings Menu | NO ONE |  |  | NEVER |  | Test Plan 8 |  |  | 1 | 0 |  |  | Not Implemented
0.4.3 | -> Dictionary | NO ONE |  |  | NEVER |  | Test Plan 9 |  |  | 1 | 0 |  |  | Not Implemented
0.4.4 | ->Financial Help Page | Jeffrey and Ryan | 4.4 | 2025-11-27 | 2025-11-27 | Unit Test | Test Plan 9 | Roy | 2025-11-28 | 0 | 0 | 4.45 | 2025-11-28