## Sheet1
CLASS 3300 INTRO TO SOFTWARE ENGINEERING
TEAM: | Monetally
SCHEDULER: | Ryan Rupakheti
DATE: | 2025-11-25
PROJECT WEEKLY SCHEDULE
ITEM | Start Date | End Date | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08
Project Idea | 2025-09-15 | 2025-09-15 | Done
Creating Requirements | 2025-09-16 | 2025-09-16 | Done
Midterm Presentation | 2025-10-29 | 2025-10-08 |  |  | Start | Done
Scrum 1/UI Development and Testing and Account System
UI Development | 2025-10-03 | 2025-10-10 |  |  | Start | Done
UI Testing and Debugging | 2025-10-11 | 2025-10-14 |  |  |  | Start | Done
Account System | 2025-10-11 | 2025-10-14 |  |  |  | Start | Done
Account Testing | 2025-10-14 | 2025-10-16 |  |  |  |  | Start | Done
Scrum 2/Implementing MVP Features and Functionality
Setup Page | 2025-10-18 | 2025-10-23 |  |  |  |  | Start | Done
Setup Page Testing | 2025-10-22 | 2025-10-26 | [5 empty] | Start | Done
Notfications System | 2025-10-18 | 2025-10-25 |  |  |  |  | Start | Done
Notication Testing | 2025-10-26 | 2025-10-30 | [5 empty] | Start | Done
Income and Expense Page | 2025-10-18 | 2025-10-25 |  |  |  |  | Start | Done
Testing for I and E Page | 2025-10-26 | 2025-11-03 | [5 empty] | Start |  | Done | (Delayed by 2 Days)
Scrum 3/Implemenating Remaining MVP Features,Deciding Misc Features,Finalzing Documenation
Deciding Misc Features | 2025-11-01 | 2025-11-01 | [7 empty] | Start/Done
Distrubutions Page | 2025-11-01 | 2025-11-06 | [7 empty] | Start | Done
Distrubutions Testing | 2025-11-06 | 2025-11-10 | [7 empty] | Start | Done
Home Page | 2025-11-12 | 2025-11-22 | [8 empty] | Start | Done
Home Page Testing | 2025-11-23 | 2025-11-26 | [9 empty] | Start | Done
Financial Help Page | 2025-11-23 | 2025-11-25 | [9 empty] | Start | Done
Financial Help Page Testing | 2025-11-25 | 2025-11-27 | [10 empty] | Start | Done
Finalizing Documenation and Licensing | 2025-11-10 | 2025-11-28 | [8 empty] | Start |  |  | Done
Final Presentation | 2025-12-01 | 2025-12-01 | [11 empty] | Start/Done